## 12.23-1.5
| Period |  | Dec 23 - Jan 5 |  |  |  | Sprint 11
| Name | ID | Role | Total Days | Holidays | Planned leave | Total work days | Total Work hours | Meeting / Training | Total Productive hours
| Ro | 1234 | Product Owner | 10 |  |  | N/A | N/A | N/A | N/A
| Sa | 12345 | Co-Product Owner | 10 |  |  | N/A | N/A | N/A | N/A
| Sw | 23456 | Scrum Master | 10 |  |  | N/A | N/A | N/A | N/A
| Br | 34567 | Business Analyst | 10 |  |  | N/A | N/A | N/A | N/A
Team | Je | 45678 | Developer | 10 | 3 | 6 | 1 | 8 | 2 | 6
| Na | 56789 | Developer | 10 | 2 |  | 8 | 64 | 16 | 48
| Sh | 67900 | Developer | 10 | 2 | 1 | 7 | 56 | 14 | 42
| Ra | 79011 | Developer | 10 | 2 |  | 8 | 64 | 16 | 48
| Kr | 90122 | Developer | 10 | 2 |  | 8 | 64 | 16 | 48
| An | 101233 | Developer | 10 | 2 | 1 | 7 | 56 | 14 | 42
[9 empty] | Total | 234
Un planned
Sprint 11:
| Je | 0
| Na | 0 | [5 empty] | Story Points Committed |  | 36 | 7.3793
| Sh | 0 | [5 empty] | Story Points Completed |  | 29
| Ra | 0 | [5 empty] | Sprint 10 Capacity : |  | 214
| Kr | 0
An

## 1.6-1.20
| Period |  | Jan 6 - Jan 20 |  |  |  | Sprint 13
| Name | ID | Role | Total Days | Holidays | Planned leave | Total work days | Total Work hours | % Project Allocation | Meeting / Training | Total Productive hours
| Ro | 1234 | Product Owner | 10 |  |  | N/A | N/A | 1 | N/A | N/A
| Sa | 12345 | Business POC | 10 |  |  | N/A | N/A | 1 | N/A | N/A
| Sw | 23456 | Scrum Master | 10 |  |  | N/A | N/A | 1 | N/A | N/A
| Br | 34567 | Business Analyst | 10 |  |  | N/A | N/A | 1 | N/A | N/A
Team | Je | 45678 | Developer | 10 | 1 |  | 9 | 72 | 0.25 | 18 | 13.5
| Na | 56789 | Developer | 0 |  |  | 0 | 0 | 0 | 0 | 0
| Sh | 67900 | Developer | 10 | 2 |  | 8 | 64 | 0.5 | 16 | 24
| Ra | 79011 | Developer | 10 | 2 |  | 8 | 64 | 0.5 | 16 | 24
| Kr | 90122 | Developer | 10 | 2 | 2 | 6 | 48 | 1 | 12 | 36
| An | 101233 | Developer | 10 | 2 | 2 | 6 | 48 | 0.5 | 12 | 18
[10 empty] | Total | 115.5
Un planned
Sprint 12:
| Je | 0
| Na | 0 | [6 empty] | Story Points Committed |  | 22 | % Completed | 72.73%
| Sh | 0 | [6 empty] | Story Points Completed |  | 16 | complete a story point | 14.625
| Ra | 0 | [6 empty] | Sprint 11 Capacity (Hours) |  | 234
| Kr | 0
An